## Sheet1
ENGR489 Gantt Chart
Niels Clayton - Self Tuning Buck Converter
Month | May |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October
Week Beginning | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18
Phase 1: Sensing Element Design
Sensing Element Background Research
Sensing Element Component Selection
Final PCB Design
Phase 2: Control System Design
Control System Background Research
Control System Design and Implementation
Phase 3: Implementation and Evaluation
Sensing Component Verification
Integration of Project Sections
Evaluation
Reports
Presentation Preperation
Final Report Writing
Deadlines | [14 empty] | Draft Final Report - 03/09 |  |  |  |  | Final Report - 08/10
[5 empty] | Mid Year Break | [7 empty] | Mid Trimester Break | [7 empty] | Presentations - 15/10