## Sheet1
ENGR489 Gantt Chart
Niels Clayton - Self Tuning Buck Converter
Month | March |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October
Week Beginning | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11
Phase 1 - Research & Setup
Literature Review | bar: March 22 to April 12
Component Selection/Purchase | bar: April 12 to April 19
Buck Converter Dev Board Design | bar: April 12 to April 19
Phase 2 - Design
PWM Generation Testing & Evaluation | bar: April 26 to June 7
Feedback Sensor Testing & Evaluation | bar: May 10 to June 7
Complete Hardware Selection | bar: May 31 to June 21
Phase 3 - Implementation
Controller Implementation | bar: June 21 to July 19
Final PCB Design | bar: July 5 to July 26
Evaluation | bar: July 26 to September 13
Reports
Preliminary Report Writing | bar: April 26 to May 17
Presentation Preperation | bar: September 13 to October 4
Final Report Writing | bar: July 26 to October 4
Deadlines | May 17: Prelim. Report - 24/05; June 28: Mid Year Break; August 30: Draft Final Report - 03/09; October 4: Final Report - 08/10
Presentations - 15/10